## Foglio1
Project Name |  |  |  | Project Manager |  |  | Start Date | End Date | Overall Progress | Project Deliverable
Application for Task Automation |  |  |  | GRUPPO 11 (I-Z) |  |  | 2023-11-20 | 2023-11-26 | --% | First prototype
Sprint Planning - 1° Settimana
Task ID | Durata (in ore) | Priority | Story Points |  | Responsabile |  | Status
1 | 10 | Massima | 10 |  | Miriam Valentino, Antony Storti, Paola Saggiomo |  | Not Started
2 | 3 | Alta | 3 |  | Paola Saggiomo |  | Not Started
3 | 8 | Alta | 8 |  | Antony Storti |  | Not Started
4 | 5 | Alta | 5 |  | Miriam Valentino |  | Not Started
5 | 3 | Alta | 3 |  | Miriam Valentino |  | Not Started
6 | 2 | Alta | 2 |  | Antony Storti |  | Not Started
7 | 2 | Alta | 2 |  | Paola Saggiomo |  | Not Started
8 | 2 | Alta | 2 |  | Paola Saggiomo |  | Not Started
9 | 3 | Alta | 3 |  | Miriam Valentino |  | Not Started
10 | 3 | Alta | 3 |  | Paola Saggiomo |  | Not Started
N.B.
1 Story Point = 1 ora di lavoro